## Time Sheet
Time sheet
Quizzion
Group: DH2IV.a6
Date | Task | Worked on | Employee | Hours | Description
2020-05-04 | MEETING-Project work/meetings | Review | Vladyslav Petrykov | 2 | Kick off
2020-05-04 | MEETING-Project work/meetings | Review | Victor Hubbers | 2 | Kick off
2020-05-04 | MEETING-Project work/meetings | Review | Vy Tran | 2 | Kick off
2020-05-04 | MEETING-Project work/meetings | Review | Katarzyna Strozykowska | 2 | Kick off
2020-05-04 | MEETING-Project work/meetings | Review | Mark Kravchuk | 2 | Kick off
2020-05-04 | MEETING-Project work/meetings | Review | Tien Thai | 2 | Kick off
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | -------------- | -----------------------------------------------------------------------------------
2020-05-05 | MEETING-Project work/meetings | Review | Tien Thai | 1 | Preparing for sprint meeting
2020-05-05 | START-Startup of project | Research | Tien Thai | 6 | Learning Vuejs+ vuex+quasar
2020-05-05 | START-Startup of project | Research | Katarzyna Strozykowska | 6 | Learning about Vue.js
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | -------------- | -----------------------------------------------------------------------------------
2020-05-06 | DOC-0.1-Plan of Approach | Documentation | Tien Thai | 2 | Initial setup
2020-05-06 | MEETING-Project work/meetings | Review | Victor Hubbers | 1 | Discussing questions for client meeting
2020-05-06 | MEETING-Project work/meetings | Review | Vy Tran | 1 | Discussing questions for client meeting
2020-05-06 | MEETING-Project work/meetings | Review | Katarzyna Strozykowska | 1 | Discussing questions for client meeting
2020-05-06 | MEETING-Project work/meetings | Review | Vladyslav Petrykov | 1 | Discussing questions for client meeting
2020-05-06 | MEETING-Project work/meetings | Review | Tien Thai | 2 | Discussing questions for client meeting + meeting report
2020-05-06 | MEETING-Project work/meetings | Review | Mark Kravchuk | 1 | Discussing questions for client meeting
2020-05-06 | START-Startup of project | Research | Victor Hubbers | 2 | Learning about Quasar
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | -------------- | -----------------------------------------------------------------------------------
2020-05-07 | MEETING-Project work/meetings | Review | Tien Thai | 2 | Discussing questions for client meeting
2020-05-07 | MEETING-Project work/meetings | Review | Victor Hubbers | 2 | Discussing questions for client meeting
2020-05-07 | MEETING-Project work/meetings | Review | Vy Tran | 2 | Discussing questions for client meeting
2020-05-07 | MEETING-Project work/meetings | Review | Katarzyna Strozykowska | 2 | Discussing questions for client meeting
2020-05-07 | MEETING-Project work/meetings | Documentation | Vladyslav Petrykov | 3 | Discussing questions for client meeting / backlog / prtoject scope
2020-05-07 | MEETING-Project work/meetings | Review | Mark Kravchuk | 2 | Discussing questions for client meeting
2020-05-07 | START-Startup of project | Research | Katarzyna Strozykowska | 2 | Learning about Vue.js
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | -------------- | -----------------------------------------------------------------------------------
2020-05-08 | MEETING-Project work/meetings | Review | Tien Thai | 1 | Kick off with client
2020-05-08 | MEETING-Project work/meetings | Review | Victor Hubbers | 1 | Kick off with client
2020-05-08 | MEETING-Project work/meetings | Review | Vladyslav Petrykov | 1 | Kick off with client
2020-05-08 | MEETING-Project work/meetings | Review | Mark Kravchuk | 1 | Kick off with client
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | -------------- | -----------------------------------------------------------------------------------
2020-05-09 | MEETING-Project work/meetings | Review | Vy Tran | 0.5 | Watch the record Kick off with client
2020-05-09 | MEETING-Project work/meetings | Review | Katarzyna Strozykowska | 0.5 | Watch the record Kick off with client
2020-05-09 | MEETING-Project work/meetings | Review | Victor Hubbers | 2 | Divided tasks for sprint 0
2020-05-09 | MEETING-Project work/meetings | Review | Vy Tran | 2 | Divided tasks for sprint 0
2020-05-09 | MEETING-Project work/meetings | Review | Katarzyna Strozykowska | 2 | Divided tasks for sprint 0
2020-05-09 | MEETING-Project work/meetings | Review | Vladyslav Petrykov | 2 | Divided tasks for sprint 0
2020-05-09 | MEETING-Project work/meetings | Review | Mark Kravchuk | 2 | Divided tasks for sprint 0
2020-05-09 | MEETING-Project work/meetings | Review | Tien Thai | 1 | Meeting report
2020-05-09 | MEETING-Project work/meetings | Review | Tien Thai | 2 | Divided tasks for sprint 0
2020-05-09 | START-Startup of project | Research | Katarzyna Strozykowska | 3 | Learning about Vue.js and Vuex
2020-05-09 | XTRA-20%-Testing | Research | Victor Hubbers | 2 | Research on testing a Vue app, and using AWS to do so
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | -------------- | -----------------------------------------------------------------------------------
2020-05-10 | DOC-0.1-Plan of Approach | Documentation | Tien Thai | 1 | Scope and Quality management
2020-05-10 | START-Startup of project | Research | Tien Thai | 1 | Researching about UX
2020-05-10 | START-Startup of project | Research | Mark Kravchuk | 5 | Did part of research about websockets and demo project for it
2020-05-10 | DOC-1.2-Technical design | Documentation | Victor Hubbers | 2 | Made version high level system design
2020-05-10 | DOC-0.1-Plan of Approach | Documentation | Katarzyna Strozykowska | 1 | Anylysing and writing about possible risks + how to prevent
2020-05-10 | START-Startup of project | Research | Katarzyna Strozykowska | 3 | Researching about WebSockets
2020-05-10 | START-Startup of project | Research | Vladyslav Petrykov | 1 | Research on AWS amazon testing
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-05-11 | DOC-1.2-Technical design | Documentation | Victor Hubbers | 1 | Put system overview in technical design with minimal explanation
2020-05-11 | XTRA-20%-Testing | Research | Victor Hubbers | 6 | Research on testing + playing around with it in a quasar demo app
2020-05-11 | DOC-1.1-Functional design | Design | Vy Tran | 5 | Mockup design
2020-05-11 | DOC-1.1-Functional design | Design | Tien Thai | 5 | Mockup design
2020-05-11 | START-Startup of project | Research | Katarzyna Strozykowska | 6 | Learning about Vue.js and Quasar
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-05-12 | MEETING-Project work/meetings | Review | Victor Hubbers | 2 | Meeting with Paul & discussing progress/next steps
2020-05-12 | MEETING-Project work/meetings | Review | Vy Tran | 2 | Meeting with Paul & discussing progress/next steps
2020-05-12 | MEETING-Project work/meetings | Review | Vladyslav Petrykov | 2 | Meeting with Paul & discussing progress/next steps
2020-05-12 | MEETING-Project work/meetings | Review | Katarzyna Strozykowska | 2 | Meeting with Paul & discussing progress/next steps
2020-05-12 | MEETING-Project work/meetings | Review | Tien Thai | 2 | Meeting with Paul & discussing progress/next steps
2020-05-12 | MEETING-Project work/meetings | Review | Mark Kravchuk | 2 | Meeting with Paul & discussing progress/next steps
2020-05-12 | DOC-1.1-Functional design | Design | Vy Tran | 2 | Mockup design
2020-05-12 | DOC-1.1-Functional design | Design | Tien Thai | 2 | Mockup design
2020-05-12 | START-Startup of project | Research | Victor Hubbers | 3 | Finalising v1 of Testing research document
2020-05-12 | START-Startup of project | Research | Katarzyna Strozykowska | 3 | Learning about Vue.js and Quasar
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-05-13 | MEETING-Project work/meetings | Review | Vladyslav Petrykov | 2.5 | Meeting with Kris & meeting with team
2020-05-13 | MEETING-Project work/meetings | Review | Victor Hubbers | 2 | Meeting with Kris & meeting with team
2020-05-13 | DOC-0.1-Plan of Approach | Documentation | Victor Hubbers | 1 | Reviewing and extending the requirements table
2020-05-13 | MEETING-Project work/meetings | Review | Katarzyna Strozykowska | 2 | Meeting with Kris & meeting with team
2020-05-13 | DOC-0.1-Plan of Approach | Documentation | Katarzyna Strozykowska | 1 | Updating user stories
2020-05-13 | DOC-0.1-Plan of Approach | Documentation | Mark Kravchuk | 2 | Updating backlog and adding content for Implementation HBO competence
2020-05-13 | MEETING-Project work/meetings | Review | Mark Kravchuk | 2 | Meeting with team and then client
2020-05-13 | MEETING-Project work/meetings | Review | Vy Tran | 2 | Meeting with Kris & meeting with team
2020-05-13 | DOC-0.1-Plan of Approach | Documentation | Tien Thai | 1 | Reviewing and extending the requirements table
2020-05-13 | MEETING-Project work/meetings | Review | Tien Thai | 2 | Meeting with team and then client
2020-05-13 | DOC-0.1-Plan of Approach | Documentation | Vy Tran | 1 | Updating user stories
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-05-14 | MEETING-Project work/meetings | Review | Katarzyna Strozykowska | 1 | Meeting with Paul & discussing progress/next steps
2020-05-14 | DOC-0.1-Plan of Approach | Documentation | Katarzyna Strozykowska | 2 | Updating user stories
2020-05-14 | MEETING-Project work/meetings | Review | Victor Hubbers | 1 | Meeting with Paul & discussing progress/next steps
2020-05-14 | DOC-0.1-Plan of Approach | Documentation | Victor Hubbers | 2 | Updating user stories
2020-05-14 | MEETING-Project work/meetings | Review | Tien Thai | 1 | Meeting with Paul & discussing progress/next steps
2020-05-14 | DOC-0.1-Plan of Approach | Documentation | Tien Thai | 1 | Adding software analysis competence
2020-05-14 | MEETING-Project work/meetings | Review | Vy Tran | 1 | Meeting with Paul & discussing progress/next steps
2020-05-14 | DOC-0.1-Plan of Approach | Documentation | Vy Tran | 1 | Adding software analysis competence
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-05-16 | MEETING-Project work/meetings | Documentation | Mark Kravchuk | 1 | Rewriting a backlog requirements according to the updated user stories
2020-05-16 | MEETING-Project work/meetings | Documentation | Vladyslav Petrykov | 1 | Rewriting a backlog requirements according to the updated user stories
2020-05-16 | MEETING-Project work/meetings | Documentation | Vy Tran | 3 | Reviewing and extending user stories/requirements
2020-05-16 | MEETING-Project work/meetings | Documentation | Tien Thai | 3 | Reviewing and extending user stories/requirements
2020-05-16 | MEETING-Project work/meetings | Documentation | Katarzyna Strozykowska | 3 | Reviewing and extending user stories/requirements
2020-05-16 | MEETING-Project work/meetings | Documentation | Victor Hubbers | 3 | Reviewing and extending user stories/requirements
2020-05-16 | MEETING-Project work/meetings | Documentation | Vladyslav Petrykov | 2 | Reviewing and extending user stories/requirements
2020-05-16 | MEETING-Project work/meetings | Documentation | Mark Kravchuk | 3 | Reviewing and extending user stories/requirements
2020-05-16 | START-Startup of project | Research | Vy Tran | 3 | Learning about Vue
2020-05-16 | START-Startup of project | Research | Katarzyna Strozykowska | 3 | Learning about Vue.js
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-05-18 | MEETING-Project work/meetings | Review | Victor Hubbers | 2 | Start sprint 1, dividing tasks
2020-05-18 | US-17-Login screen | Implementation | Vy Tran | 3 | Login page frontend
2020-05-18 | MEETING-Project work/meetings | Review | Vy Tran | 2 | Start sprint 1, dividing tasks
2020-05-18 | MEETING-Project work/meetings | Review | Vladyslav Petrykov | 2 | Start sprint 1, dividing tasks
2020-05-18 | MEETING-Project work/meetings | Review | Katarzyna Strozykowska | 2 | Start sprint 1, dividing tasks
2020-05-18 | MEETING-Project work/meetings | Review | Tien Thai | 2 | Start sprint 1, dividing tasks
2020-05-18 | MEETING-Project work/meetings | Review | Mark Kravchuk | 2 | Start sprint 1, dividing tasks
2020-05-18 | DOC-0.1-Plan of Approach | Documentation | Mark Kravchuk | 1 | Added company background for the PoA (14.05.2020)
2020-05-18 | START-Startup of project | Research | Mark Kravchuk | 7 | Learning Vue from scratch
2020-05-18 | US-14-Answering questions | Implementation | Victor Hubbers | 5 | Start with frontend for answering questions page
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-05-19 | US-9-Creating dashboard | Implementation | Katarzyna Strozykowska | 3 | Front-end for dashboard page, without functionality
2020-05-19 | MEETING-Project work/meetings | Review | Victor Hubbers | 1 | Meeting with Paul & discussing progress/next steps
2020-05-19 | US-17-Login screen | Implementation | Vy Tran | 2 | Login page frontend
2020-05-19 | MEETING-Project work/meetings | Review | Vy Tran | 1 | Meeting with Paul & discussing progress/next steps
2020-05-19 | MEETING-Project work/meetings | Review | Vladyslav Petrykov | 1 | Meeting with Paul & discussing progress/next steps
2020-05-19 | MEETING-Project work/meetings | Review | Katarzyna Strozykowska | 1 | Meeting with Paul & discussing progress/next steps
2020-05-19 | MEETING-Project work/meetings | Review | Tien Thai | 1 | Meeting with Paul & discussing progress/next steps
2020-05-19 | MEETING-Project work/meetings | Review | Mark Kravchuk | 1 | Meeting with Paul & discussing progress/next steps
2020-05-19 | MEETING-Project work/meetings | Review | Vladyslav Petrykov | 1 | Meeting with Paul & discussing progress/next steps
2020-05-19 | START-Startup of project | Research | Katarzyna Strozykowska | 3 | Learning about Quasar Framework.
2020-05-19 | US-14-Answering questions | Implementation | Victor Hubbers | 2 | Front end for answering page
2020-05-19 | START-Startup of project | Research | Mark Kravchuk | 8 | Finishing learning Vue js and starting learning Quasar
2020-05-19 | US-1-Creating quiz | Implementation | Tien Thai | 3 | Front end for creating quiz page
2020-05-19 | START-Startup of project | Research | Vladyslav Petrykov | 2 | Vue.js
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-05-20 | MEETING-Project work/meetings | Review | Victor Hubbers | 1 | Stand-up meeting
2020-05-20 | MEETING-Project work/meetings | Review | Vladyslav Petrykov | 1 | Stand-up meeting
2020-05-20 | MEETING-Project work/meetings | Review | Katarzyna Strozykowska | 1 | Stand-up meeting
2020-05-20 | MEETING-Project work/meetings | Review | Tien Thai | 1 | Stand-up meeting
2020-05-20 | US-17-Login screen | Implementation | Vy Tran | 3 | Login page frontend
2020-05-20 | MEETING-Project work/meetings | Review | Vy Tran | 1 | Stand-up meeting
2020-05-20 | MEETING-Project work/meetings | Review | Mark Kravchuk | 4 | Stand-up meeting and learning quasar
2020-05-20 | START-Startup of project | Research | Katarzyna Strozykowska | 3 | Learning about Quasar Framework.
2020-05-20 | US-1-Creating quiz | Implementation | Tien Thai | 3.5 | Restructure front end for create quiz page + improvising overall look
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-05-21 | START-Startup of project | Research | Vladyslav Petrykov | 4.5 | Vue js
2020-05-21 | US-17-Login screen | Implementation | Vy Tran | 3.5 | Login page frontend
2020-05-21 | DOC-1.1-Functional design | Design | Tien Thai | 6 | User interface design + added screens
2020-05-21 | US-1-Creating quiz | Implementation | Tien Thai | 2 | Frontend implementation + improvising
2020-05-21 | US-9-Creating dashboard | Implementation | Katarzyna Strozykowska | 6 | Improving the front-end + basic functionality for Dashboard
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-05-22 | START-Startup of project | Research | Vladyslav Petrykov | 9 | Quasar(4)/ Vuex(2)/ frontend adding quiz(3)
2020-05-22 | START-Startup of project | Research | Mark Kravchuk | 4 | Learning Vuex and Quasar
2020-05-22 | START-Startup of project | Research | Vy Tran | 4 | Learn Vuex
2020-05-22 | US-14-Answering questions | Implementation | Victor Hubbers | 2 | Added background and fixed couple styling issues
2020-05-22 | DOC-1.1-Functional design | Design | Tien Thai | 2 | Prototyping +added screen adjustment
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-05-23 | MEETING-Project work/meetings | Review | Victor Hubbers | 1 | Stand-up meeting
2020-05-23 | US-17-Login screen | Implementation | Vy Tran | 2 | Fix Carousel Image Login Page
2020-05-23 | MEETING-Project work/meetings | Review | Vy Tran | 1 | Stand-up meeting
2020-05-23 | MEETING-Project work/meetings | Review | Vladyslav Petrykov | 1 | Stand-up meeting
2020-05-23 | MEETING-Project work/meetings | Review | Katarzyna Strozykowska | 1 | Stand-up meeting
2020-05-23 | MEETING-Project work/meetings | Review | Tien Thai | 1 | Stand-up meeting
2020-05-23 | MEETING-Project work/meetings | Review | Mark Kravchuk | 1 | Stand-up meeting
2020-05-23 | US-6-Adding multiple choice questions | Implementation | Vladyslav Petrykov | 2 | Frontend + basic functionality
2020-05-23 | US-1-Creating quiz | Implementation | Tien Thai | 3 | Frontend
2020-05-23 | US-6-Adding multiple choice questions | Implementation | Mark Kravchuk | 2 | Frontend + basic functionality
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-05-24 | US-9-Creating dashboard | Implementation | Katarzyna Strozykowska | 4 | Combining components + sidebar
2020-05-24 | US-1-Creating quiz | Implementation | Tien Thai | 4 | Combining components + improving the styling
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-05-25 | MEETING-Project work/meetings | Review | Victor Hubbers | 1 | Stand-up meeting
2020-05-25 | US-13-Result screen for moderator | Implementation | Vy Tran | 3 | Result screen frontend
2020-05-25 | MEETING-Project work/meetings | Review | Vy Tran | 1 | Stand-up meeting
2020-05-25 | MEETING-Project work/meetings | Review | Vladyslav Petrykov | 1 | Stand-up meeting
2020-05-25 | MEETING-Project work/meetings | Review | Katarzyna Strozykowska | 1 | Stand-up meeting
2020-05-25 | MEETING-Project work/meetings | Review | Tien Thai | 1 | Stand-up meeting
2020-05-25 | MEETING-Project work/meetings | Review | Mark Kravchuk | 1 | Stand-up meeting
2020-05-25 | DOC-1.1-Functional design | Design | Tien Thai | 2 | Design extra screens (user enter name)
2020-05-25 | US-1-Creating quiz | Implementation | Tien Thai | 2.5 | Implement function for dashboard+add quiz
2020-05-25 | START-Vuex version 0 | Implementation | Victor Hubbers | 7 | Making version 0 of Vuex store
2020-05-25 | START-Startup of project | Implementation | Katarzyna Strozykowska | 4 | Making extra page for invitation
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-05-26 | START-Startup of project | Implementation | Victor Hubbers | 2 | Making version 0 of Vuex store
2020-05-26 | MEETING-Project work/meetings | Review | Victor Hubbers | 2 | Meeting with Paul + resolving merge conflicts + discussing next steps
2020-05-26 | MEETING-Project work/meetings | Review | Vy Tran | 2 | Meeting with Paul + resolving merge conflicts + discussing next steps
2020-05-26 | MEETING-Project work/meetings | Review | Vladyslav Petrykov | 2 | Meeting with Paul + resolving merge conflicts + discussing next steps
2020-05-26 | MEETING-Project work/meetings | Review | Katarzyna Strozykowska | 2 | Meeting with Paul + resolving merge conflicts + discussing next steps
2020-05-26 | MEETING-Project work/meetings | Review | Tien Thai | 2 | Meeting with Paul + resolving merge conflicts + discussing next steps
2020-05-26 | START-Startup of project | Implementation | Katarzyna Strozykowska | 3 | Working on extra page for invitation
2020-05-26 | MEETING-Project work/meetings | Review | Mark Kravchuk | 2 | Meeting with Paul + resolving merge conflicts + discussing next steps
2020-05-26 | START-Startup of project | Review | Mark Kravchuk | 3 | Fixing bugs after merging
2020-05-25 | START-Startup of project | Implementation | Mark Kravchuk | 2 | Merging everyone`s functionality
2020-05-26 | US-13-Result screen for moderator | Implementation | Vy Tran | 3 | Result screen frontend
2020-05-24 | US-6-Adding multiple choice questions | Implementation | Mark Kravchuk | 2 | Adding timer and fixing layouts
2020-05-26 | START-Startup of project | Implementation | Vladyslav Petrykov | 2 | Fixing bugs after merging
2020-05-26 | START-Vuex version 0 | Implementation | Victor Hubbers | 7 | Making version 0 of Vuex store
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-05-27 | START-Startup of project | Implementation | Vladyslav Petrykov | 1 | Fixing bugs after merging
2020-05-27 | MEETING-Project work/meetings | Review | Victor Hubbers | 2 | Stand-up meeting + meeting with Kris
2020-05-27 | MEETING-Project work/meetings | Review | Vy Tran | 2 | Stand-up meeting + meeting with Kris
2020-05-27 | MEETING-Project work/meetings | Review | Vladyslav Petrykov | 2 | Stand-up meeting + meeting with Kris
2020-05-27 | START-Startup of project | Research | Tien Thai | 2 | Work through backend api doc from client
2020-05-27 | MEETING-Project work/meetings | Review | Katarzyna Strozykowska | 2 | Stand-up meeting + meeting with Kris
2020-05-27 | MEETING-Project work/meetings | Review | Tien Thai | 2 | Stand-up meeting + meeting with Kris
2020-05-27 | MEETING-Project work/meetings | Review | Mark Kravchuk | 2 | Stand-up meeting + meeting with Kris
2020-05-27 | US-5 Implement invitation screen | Implementation | Katarzyna Strozykowska | 3 | Finishing the frontend of the invitation screen
2020-05-27 | US-14-Answering questions | Implementation | Victor Hubbers | 4 | Implementing Vuex + next questions/results button
2020-05-27 | US-6-Adding multiple choice questions | Implementation | Vladyslav Petrykov | 1 | adding vuex to the page
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-05-28 | MEETING-Project work/meetings | Review | Victor Hubbers | 2 | Meeting with Paul + stand-up meeting (discussing gitlab boards/issues)
2020-05-28 | MEETING-Project work/meetings | Review | Vy Tran | 2 | Meeting with Paul + stand-up meeting (discussing gitlab boards/issues)
2020-05-28 | MEETING-Project work/meetings | Review | Vladyslav Petrykov | 2 | Meeting with Paul + stand-up meeting (discussing gitlab boards/issues)
2020-05-28 | MEETING-Project work/meetings | Review | Katarzyna Strozykowska | 2 | Meeting with Paul + stand-up meeting (discussing gitlab boards/issues)
2020-05-28 | US-13-Result screen for moderator | Implementation | Vy Tran | 3 | Result screen frontend
2020-05-28 | MEETING-Project work/meetings | Review | Tien Thai | 2 | Meeting with Paul + stand-up meeting (discussing gitlab boards/issues)
2020-05-28 | MEETING-Project work/meetings | Review | Mark Kravchuk | 2 | Meeting with Paul + stand-up meeting (discussing gitlab boards/issues)
2020-05-28 | US-9-Creating dashboard | Implementation | Victor Hubbers | 3 | all data is now loaded from vuex
2020-05-28 | START-Startup of project | Research | Katarzyna Strozykowska | 2.5 | Working on the first version of API calls
2020-05-28 | US-2-Edit quiz | Implementation | Tien Thai | 5.5 | Implementing frontend + dashboard get link
2020-05-28 | START-Startup of project | Research | Mark Kravchuk | 2.5 | Researching the backend of Parantion company
2020-05-28 | US-6-Adding multiple choice questions | Implementation | Vladyslav Petrykov | 3 | adding vuex + design fixes
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-05-29 | MEETING-Project work/meetings | Review | Victor Hubbers | 1 | Stand-up meeting
2020-05-29 | US-13-Result screen for moderator | Implementation | Vy Tran | 3 | Result screen frontend
2020-05-29 | MEETING-Project work/meetings | Review | Vy Tran | 1 | Stand-up meeting
2020-05-29 | MEETING-Project work/meetings | Review | Vladyslav Petrykov | 1 | Stand-up meeting
2020-05-29 | MEETING-Project work/meetings | Review | Mark Kravchuk | 1 | Stand-up meeting
2020-05-29 | US-6-Adding multiple choice questions | Implementation | Vladyslav Petrykov | 1 | adding vuex
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-05-30 | MEETING-Project work/meetings | Review | Tien Thai | 0.5 | Backend meeting
2020-05-30 | US-13-Result screen for moderator | Implementation | Vy Tran | 3 | Result screen frontend- scrolling bar implemetation
2020-05-30 | MEETING-Project work/meetings | Review | Mark Kravchuk | 0.5 | Backend meeting
2020-05-30 | MEETING-Project work/meetings | Review | Katarzyna Strozykowska | 0.5 | Backend meeting
2020-05-30 | US-5 Implement invitation screen | Implementation | Tien Thai | 2 | Fixing frontend bugs
2020-05-30 | US-2-Edit quiz | Implementation | Tien Thai | 4.5 | Fixing frontend bugs
2020-05-30 | START-Startup of project | Implementation | Katarzyna Strozykowska | 2 | Fixing colors
2020-05-30 | US-9-Creating dashboard | Implementation | Katarzyna Strozykowska | 4 | Working on the dashboard page, fixing bugs
2020-05-30 | US-6-Adding multiple choice questions | Implementation | Vladyslav Petrykov | 2 | adding vuex
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-05-31 | US-1-Creating quiz | Implementation | Tien Thai | 1 | Adding Vuex to create quiz
2020-05-31 | US-2-Edit quiz | Implementation | Tien Thai | 1 | Fixing delete quiz function
2020-05-31 | Backend-backend for the project | Implementation | Katarzyna Strozykowska | 1 | Testing the backend of Parantion, researching about multiple API requests
2020-05-31 | US-9-Creating dashboard | Implementation | Victor Hubbers | 4 | Merging/resolving conflicts/bugs
2020-05-31 | US-5 Implement invitation screen | Implementation | Victor Hubbers | 1 | Adding Vuex to invitation screee
2020-05-31 | Backend-backend for the project | Implementation | Katarzyna Strozykowska | 2 | Basic API for quiz
2020-05-31 | Backend-backend for the project | Implementation | Mark Kravchuk | 4 | GET and POST (not working) requests for questions
2020-05-31 | US-6-Adding multiple choice questions | Implementation | Vladyslav Petrykov | 1 | adding vuex
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-06-01 | US-17-backend-Login/logout functionality | Implementation | Tien Thai | 2.5 | Adding Login and logout api
2020-06-01 | US-5 Implement invitation screen | Implementation | Tien Thai | 0.5 | Adding working invite link + add dashboard to side nav
2020-06-01 | Backend-backend for the project | Implementation | Katarzyna Strozykowska | 1 | Improving the API calls for the quiz
2020-06-01 | Backend-backend for the project | Implementation | Mark Kravchuk | 4 | POST (working) PUT (not working) DELETE added for questions in backend
2020-06-01 | MEETING-Project work/meetings | Implementation | Vladyslav Petrykov | 2 | documentation / general structure of document in teams
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-06-02 | MEETING-Project work/meetings | Review | Katarzyna Strozykowska | 3 | Discussed new sprint plans and general progress + Meeting with Paul
2020-06-02 | MEETING-Project work/meetings | Review | Tien Thai | 3 | Discussed new sprint plans and general progress + Meeting with Paul
2020-06-02 | MEETING-Project work/meetings | Review | Mark Kravchuk | 3 | Discussed new sprint plans and general progress + Meeting with Paul
2020-06-02 | MEETING-Project work/meetings | Review | Vy Tran | 3 | Discussed new sprint plans and general progress + Meeting with Paul
2020-06-02 | MEETING-Project work/meetings | Review | Vladyslav Petrykov | 3 | Discussed new sprint plans and general progress + Meeting with Paul
2020-06-02 | MEETING-Project work/meetings | Review | Victor Hubbers | 3 | Discussed new sprint plans and general progress + Meeting with Paul
2020-06-02 | US-5 Implement invitation screen | Implementation | Victor Hubbers | 1 | Implemented copying link
2020-06-02 | Backend-backend for the project | Implementation | Katarzyna Strozykowska | 0.5 | Improving the API calls for the quiz, discussed possible changes
2020-06-02 | US-11 Result screen for moderator | Implementation | Vy Tran | 2.5 | Connect to vuex
2020-06-02 | US-18-Result screen for players | Implementation | Vy Tran | 3 | Create result screen for players
2020-06-02 | Backend-backend for the project | Implementation | Mark Kravchuk | 0.5 | Improving the API calls for the quiz, discussed possible changes
2020-06-02 | US-17-backend-Login/logout functionality | Implementation | Victor Hubbers | 3 | not loggedIn -> route to login page + connect Vuex action with backend
2020-06-02 | MEETING-Project work/meetings | Implementation | Vladyslav Petrykov | 5 | helping with vuex + changing vuex for quizz questions
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-06-03 | MEETING-Project work/meetings | Review | Tien Thai | 2 | Stand-up meeting and meeting with Kris
2020-06-03 | MEETING-Project work/meetings | Review | Victor Hubbers | 2 | Stand-up meeting and meeting with Kris
2020-06-03 | MEETING-Project work/meetings | Review | Vladyslav Petrykov | 2 | Stand-up meeting and meeting with Kris
2020-02-03 | US-11 Result screen for moderator | Implementation | Vy Tran | 5 | Connect to vuex
2020-06-03 | MEETING-Project work/meetings | Review | Vy Tran | 2 | Stand-up meeting and meeting with Kris
2020-06-03 | MEETING-Project work/meetings | Review | Mark Kravchuk | 2 | Stand-up meeting and meeting with Kris
2020-06-03 | MEETING-Project work/meetings | Review | Katarzyna Strozykowska | 2 | Stand-up meeting and meeting with Kris
2020-06-03 | MEETING-Project work/meetings | Implementation | Vladyslav Petrykov | 2 | finished quizz questions vuex + design changes
2020-06-03 | Backend-backend for the project | Implementation | Katarzyna Strozykowska | 2 | working on quiz api
2020-06-03 | Backend-backend for the project | Implementation | Mark Kravchuk | 3 | Finishing API calls for question CRUD operations
2020-06-03 | MEETING-Project work/meetings | Implementation | Victor Hubbers | 1 | Demo preparations + helping figure out bugs
2020-06-03 | MEETING-Project work/meetings | Review | Victor Hubbers | 2 | Give demo + divide new tasks
2020-06-03 | MEETING-Project work/meetings | Review | Katarzyna Strozykowska | 2 | Give demo + divide new tasks
2020-06-03 | MEETING-Project work/meetings | Review | Tien Thai | 2 | Give demo + divide new tasks
2020-06-03 | MEETING-Project work/meetings | Review | Vy Tran | 2 | Give demo + divide new tasks
2020-06-03 | MEETING-Project work/meetings | Review | Vladyslav Petrykov | 2 | Give demo + divide new tasks
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-06-04 | MEETING-Project work/meetings | Review | Vy Tran | 1 | Meeting with Paul + Discussing about GitLab (branches and issues)
2020-06-04 | MEETING-Project work/meetings | Review | Vladyslav Petrykov | 1 | Meeting with Paul + Discussing about GitLab (branches and issues)
2020-06-04 | MEETING-Project work/meetings | Review | Victor Hubbers | 1 | Meeting with Paul + Discussing about GitLab (branches and issues)
2020-06-04 | MEETING-Project work/meetings | Review | Katarzyna Strozykowska | 1.5 | Meeting with Paul + Discussing about GitLab (branches and issues) +backend meeting
2020-06-04 | US-13-Result screen for moderator | Implementation | Vy Tran | 2 | Connect to vuex
2020-06-04 | Backend-backend for the project | Implementation | Katarzyna Strozykowska | 6 | working on quiz api
2020-06-04 | Backend-backend for the project | Implementation | Tien Thai | 3 | working on result api
2020-06-04 | MEETING-Project work/meetings | Review | Tien Thai | 1.5 | Meeting with Paul + Discussing about GitLab (branches and issues) +backend meeting
2020-06-04 | MEETING-Project work/meetings | Review | Mark Kravchuk | 1.5 | Meeting with Paul + Discussing about GitLab (branches and issues) +backend meeting
2020-06-04 | US-7-Timing functionality | Implementation | Vladyslav Petrykov | 5 | Timer + Dashboard styling
2020-06-04 | US-7-Timing functionality | Implementation | Victor Hubbers | 5 | Timer + Dashboard- and AnswerForm styling
04.06.2020. | Backend-backend for the project | Implementation | Mark Kravchuk | 3 | creating API calls for answers (backend)
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-06-05 | US-18-Result screen for player | Implementation | Vy Tran | 7 | Frontend
2020-06-05 | MEETING-Project work/meetings | Design | Vladyslav Petrykov | 4 | animation dashboard/add quiz question. Add quiz question (responsive)
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-06-06 | MEETING-Project work/meetings | Review | Mark Kravchuk | 1 | Meeting, discussing the progress/issues with API connections
2020-06-06 | MEETING-Project work/meetings | Review | Tien Thai | 1 | Meeting, discussing the progress/issues with API connections
2020-06-06 | MEETING-Project work/meetings | Review | Katarzyna Strozykowska | 1 | Meeting, discussing the progress/issues with API connections
2020-06-06 | Backend-backend for the project | Implementation | Katarzyna Strozykowska | 5 | working on form and quiz API
2020-06-06 | Backend-backend for the project | Implementation | Mark Kravchuk | 4 | working on answers API
2020-06-06 | Backend-backend for the project | Implementation | Tien Thai | 5 | working on respondent api
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-06-07 | Backend-backend for the project | Implementation | Tien Thai | 6 | working on result api
2020-06-07 | Backend-backend for the project | Documentation | Mark Kravchuk | 1 | Documenting API for answers
2020-06-07 | DOC-1.2-Technical design | Implementation | Tien Thai | 1 | Doc for respondent api
2020-06-07 | Backend-backend for the project | Implementation | Katarzyna Strozykowska | 7 | working on quiz api, writing documentation for API and basic tests
2020-06-07 | MEETING-Project work/meetings | Implementation | Vladyslav Petrykov | 2 | responsive screens / components changes
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-06-08 | MEETING-Project work/meetings | Review | Tien Thai | 2 | stand-up meeting
2020-06-08 | MEETING-Project work/meetings | Review | Vy Tran | 2 | stand-up meeting
2020-06-08 | MEETING-Project work/meetings | Review | Vladyslav Petrykov | 2 | stand-up meeting
2020-06-08 | MEETING-Project work/meetings | Review | Victor Hubbers | 2 | stand-up meeting
2020-06-08 | MEETING-Project work/meetings | Review | Katarzyna Strozykowska | 2 | stand-up meeting
2020-06-08 | MEETING-Project work/meetings | Review | Mark Kravchuk | 2 | stand-up meeting
2020-06-08 | US-13-Result screen for moderator | Implementation | Victor Hubbers | 2 | Merging + grabbing ids from URL
2020-06-08 | Backend-backend for the project | Implementation | Vy Tran | 1.5 | Help Katarzyna with backend api
2020-06-08 | US-13-Result screen for moderator | Implementation | Vy Tran | 2 | Merging + grabbing ids from URL
2020-06-08 | Backend-backend for the project | Implementation | Katarzyna Strozykowska | 3 | Working on a PUT quiz request
2020-06-08 | CNCT-connecting backend with frontend | Implementation | Victor Hubbers | 4 | working on connection with users api and rewriting actions.
2020-06-08 | Backend-backend for the project | Implementation | Mark Kravchuk | 4 | creating automated tests for question API
2020-06-08 | CNCT-connecting backend with frontend | Implementation | Vladyslav Petrykov | 2 | working on connection with users api and rewriting actions.
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-06-09 | MEETING-Project work/meetings | Review | Vy Tran | 1.5 | Meeting with Paul + Discussing about new tasks
2020-06-09 | MEETING-Project work/meetings | Review | Vladyslav Petrykov | 1.5 | Meeting with Paul + Discussing about new tasks
2020-06-09 | MEETING-Project work/meetings | Review | Victor Hubbers | 1.5 | Meeting with Paul + Discussing about new tasks
2020-06-09 | MEETING-Project work/meetings | Review | Katarzyna Strozykowska | 1.5 | Meeting with Paul + Discussing about new tasks
2020-06-09 | MEETING-Project work/meetings | Review | Tien Thai | 1.5 | Meeting with Paul + Discussing about new tasks
2020-06-09 | MEETING-Project work/meetings | Review | Mark Kravchuk | 1.5 | Meeting with Paul + Discussing about new tasks
2020-06-09 | Websockets | Implementation | Mark Kravchuk | 2 | Doing the websocket design of the application behavior
2020-06-09 | CNCT-connecting backend with frontend | Implementation | Vy Tran | 5 | Connecting frontend with the quiz API
2020-06-09 | CNCT-connecting backend with frontend | Implementation | Victor Hubbers | 5 | Connecting frontend with the quiz API
2020-06-09 | CNCT-connecting backend with frontend | Implementation | Katarzyna Strozykowska | 5 | Connecting frontend with the quiz API
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-06-10 | MEETING-Project work/meetings | Review | Victor Hubbers | 1.5 | Stand-up meeting + meeting with Kris
2020-06-10 | MEETING-Project work/meetings | Review | Vladyslav Petrykov | 1.5 | Stand-up meeting + meeting with Kris
2020-06-10 | MEETING-Project work/meetings | Review | Vy Tran | 1.5 | Stand-up meeting + meeting with Kris
2020-06-10 | MEETING-Project work/meetings | Review | Tien Thai | 1.5 | Stand-up meeting + meeting with Kris
2020-06-10 | MEETING-Project work/meetings | Review | Katarzyna Strozykowska | 1.5 | Stand-up meeting + meeting with Kris
2020-06-10 | MEETING-Project work/meetings | Review | Mark Kravchuk | 1.5 | Stand-up meeting + meeting with Kris
2020-06-10 | CNCT-connecting backend with frontend | Review | Victor Hubbers | 1 | Connecting frontend with the question/answers API
2020-06-10 | CNCT-connecting backend with frontend | Review | Vladyslav Petrykov | 2 | Connecting frontend with the question/answers API
2020-06-10 | Backend-backend for the project | Implementation | Mark Kravchuk | 4 | Creating tests for answers API
2020-06-10 | CNCT-connecting backend with frontend | Review | Tien Thai | 2 | Connecting frontend with the question/answers API
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-06-11 | MEETING-Project work/meetings | Review | Tien Thai | 1 | Meeting with Paul + Discussing about new tasks
2020-06-11 | MEETING-Project work/meetings | Review | Vy Tran | 1 | Meeting with Paul + Discussing about new tasks
2020-06-11 | MEETING-Project work/meetings | Review | Vladyslav Petrykov | 1 | Meeting with Paul + Discussing about new tasks
2020-06-11 | MEETING-Project work/meetings | Review | Victor Hubbers | 1 | Meeting with Paul + Discussing about new tasks
2020-06-11 | MEETING-Project work/meetings | Review | Mark Kravchuk | 1 | Meeting with Paul + Discussing about new tasks
2020-06-11 | MEETING-Project work/meetings | Review | Katarzyna Strozykowska | 1 | Meeting with Paul + Discussing about new tasks
2020-06-11 | CNCT-connecting backend with frontend | Implementation | Katarzyna Strozykowska | 1 | Connecting frontend with the form API
2020-06-11 | CNCT-connecting backend with frontend | Implementation | Victor Hubbers | 1 | Connecting frontend with the form API
2020-06-11 | Image uploading | Implementation | Vy Tran | 3 | implement image uploading with base64 but failed
2020-06-11 | CNCT-connecting backend with frontend | Implementation | Vy Tran | 1 | Connecting frontend with the form API
2020-06-11 | CNCT-connecting backend with frontend | Implementation | Victor Hubbers | 6 | Cleaned database + Connected first part of respondent + Connect answer to question
2020-06-11 | CNCT-connecting backend with frontend | Implementation | Tien Thai | 6 | Cleaned database + Connected first part of respondent + Connect answer to question
2020-06-11 | CNCT-connecting backend with frontend | Review | Vladyslav Petrykov | 4 | tesing question/answers api. Fixing bugs
2020-06-11 | Backend-backend for the project | Implementation | Mark Kravchuk | 4 | changing API calls to suit for the frontend
2020-06-11 | US-6-Adding multiple choice questions | Implementation | Katarzyna Strozykowska | 4 | working on base64 and images
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-06-12 | MEETING-Project work/meetings | Review | Victor Hubbers | 2 | stand-up meeting
2020-06-12 | Image-Image uploading | Implementation | Vy Tran | 5 | Use firebase storage for storing images
2020-06-12 | MEETING-Project work/meetings | Review | Vy Tran | 2 | stand-up meeting
2020-06-12 | MEETING-Project work/meetings | Review | Mark Kravchuk | 2 | stand-up meeting
2020-06-12 | MEETING-Project work/meetings | Review | Tien Thai | 2 | stand-up meeting
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-06-13 | Image-Image uploading | Implementation | Vy Tran | 2 | Use firebase storage for storing images
2020-06-13 | US-4-Customize quiz- logo | Implementation | Katarzyna Strozykowska | 2 | Working on add/edit logo and add/edit image
2020-06-13 | US-4-Customize quiz- logo | Implementation | Vy Tran | 2 | Working on add/edit logo and add/edit image
2020-06-13 | MEETING-Project work/meetings | Review | Katarzyna Strozykowska | 2 | stand-up meeting + cleaning up the GitLab
2020-06-13 | MEETING-Project work/meetings | Review | Victor Hubbers | 2 | stand-up meeting + cleaning up the GitLab
2020-06-13 | MEETING-Project work/meetings | Review | Vy Tran | 2 | stand-up meeting + cleaning up the GitLab
2020-06-13 | MEETING-Project work/meetings | Review | Tien Thai | 2 | stand-up meeting + cleaning up the GitLab
2020-06-13 | MEETING-Project work/meetings | Review | Mark Kravchuk | 2 | stand-up meeting + cleaning up the GitLab
2020-06-13 | CNCT-connecting backend with frontend | Implementation | Victor Hubbers | 1 | implement logout functionality
2020-06-13 | Backend-backend for the project | Implementation | Mark Kravchuk | 2 | change DELETE method to suit for the frontend
2020-06-13 | CNCT-connecting backend with frontend | Implementation | Tien Thai | 1 | implement logout functionality
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-06-14 | XTRA-20%-Design | Implementation | Tien Thai | 2 | Logo design
2020-06-14 | Websocket-Doing the websocket integration | Implementation | Mark Kravchuk | 5 | Doing initial setup of websocket server, creating first verison of websocket server
2020-06-14 | XTRA-20%-Testing | Implementation | Victor Hubbers | 3 | Initial setup + config for testing + writing first test
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-06-15 | MEETING-Project work/meetings | Review | Victor Hubbers | 2 | stand-up meeting + planning for Sprint 3
2020-06-15 | MEETING-Project work/meetings | Review | Katarzyna Strozykowska | 2 | stand-up meeting + planning for Sprint 3
2020-06-15 | MEETING-Project work/meetings | Review | Vy Tran | 2 | stand-up meeting + planning for Sprint 3
2020-06-15 | MEETING-Project work/meetings | Review | Vladyslav Petrykov | 2 | stand-up meeting + planning for Sprint 3
2020-06-15 | MEETING-Project work/meetings | Review | Mark Kravchuk | 2 | stand-up meeting + planning for Sprint 3
2020-06-15 | MEETING-Project work/meetings | Review | Tien Thai | 2 | stand-up meeting + planning for Sprint 3
2020-06-15 | API-connection frontend | Implementation | Vladyslav Petrykov | 1 | Questions
2020-06-15 | API-connection frontend | Implementation | Vladyslav Petrykov | 1 | Answers
2020-06-15 | Websocket-Doing the websocket integration | Implementation | Mark Kravchuk | 6 | Creating sample project to test websocket server, fixing bugs
2020-06-15 | EXTRA-20%-ESLint | Research | Katarzyna Strozykowska | 2 | Research about ESLint
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-06-16 | MEETING-Project work/meetings | Review | Victor Hubbers | 2 | Meeting with paul + discussed planning
2020-06-16 | MEETING-Project work/meetings | Review | Katarzyna Strozykowska | 2 | Meeting with paul + discussed planning
2020-06-16 | MEETING-Project work/meetings | Review | Vy Tran | 2 | Meeting with paul + discussed planning
2020-06-16 | MEETING-Project work/meetings | Review | Vladyslav Petrykov | 2 | Meeting with paul + discussed planning
2020-06-16 | MEETING-Project work/meetings | Review | Mark Kravchuk | 2 | Meeting with paul + discussed planning
2020-06-16 | MEETING-Project work/meetings | Review | Tien Thai | 2 | Meeting with paul + discussed planning
2020-06-16 | MEETING-Project work/meetings | Documentation | Vladyslav Petrykov | 2 | Meeting with paul + discussed planning
2020-06-16 | PM-Project work/scrum board management | Project management | Vy Tran | 0.5 | Added weights to issues
2020-06-16 | Frontend-Podium | Implementation | Vy Tran | 1 | Create podium screen
2020-06-16 | Backend-backend for the project | Implementation | Vy Tran | 3 | Result api for respondents and quiz masters
2020-06-16 | Backend-backend for the project | Implementation | Tien Thai | 6 | Working on own Database for respondents
2020-06-16 | Backend-backend for the project | Implementation | Tien Thai | 3 | Result api for respondents and quiz masters
2020-06-16 | Backend-backend for the project | Implementation | Mark Kravchuk | 3 | Checked DELETE method for question API, wrote tests to verify that works
2020-06-16 | EXTRA-20%-ESLint | Documentation | Katarzyna Strozykowska | 2 | Writing basic version of the documentation about ESLint
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-06-17 | MEETING-Project work/meetings | Review | Victor Hubbers | 2.5 | Stand up + meeting with Kris + Sprint review
2020-06-17 | MEETING-Project work/meetings | Review | Katarzyna Strozykowska | 2.5 | Stand up + meeting with Kris + Sprint review
2020-06-17 | MEETING-Project work/meetings | Review | Vy Tran | 2.5 | Stand up + meeting with Kris + Sprint review
2020-06-17 | MEETING-Project work/meetings | Review | Vladyslav Petrykov | 2.5 | Stand up + meeting with Kris + Sprint review
2020-06-17 | MEETING-Project work/meetings | Review | Mark Kravchuk | 2.5 | Stand up + meeting with Kris + Sprint review
2020-06-17 | MEETING-Project work/meetings | Review | Tien Thai | 2.5 | Stand up + meeting with Kris + Sprint review
2020-06-17 | CNCT-connecting backend with frontend | Implementation | Victor Hubbers | 4.5 | Connection between respondent and our backend for answering and results
2020-06-17 | CNCT-connecting backend with frontend | Implementation | Tien Thai | 4.5 | Connection between respondent and our backend for answering and results
2020-06-17 | US-12-Statistics dashboard | Implementation | Katarzyna Strozykowska | 2 | Basic design of the statistic dashboard
2020-06-17 | XTRA-20%-Testing | Implementation | Victor Hubbers | 2 | More tests for quizzes module
2020-06-17 | Presentation-with client | Review | Vladyslav Petrykov | 1.5 | Making presentation
2020-06-17 | Presentation-with client | Review | Vy Tran | 1.5 | Making presentation
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-06-18 | MEETING-Project work/meetings | Review | Victor Hubbers | 1 | Stand up + meeting with Paul
2020-06-18 | MEETING-Project work/meetings | Review | Katarzyna Strozykowska | 1 | Stand up + meeting with Paul
2020-06-18 | MEETING-Project work/meetings | Review | Vy Tran | 1 | Stand up + meeting with Paul
2020-06-18 | MEETING-Project work/meetings | Review | Vladyslav Petrykov | 1 | Stand up + meeting with Paul
2020-06-18 | MEETING-Project work/meetings | Review | Mark Kravchuk | 1 | Stand up + meeting with Paul
2020-06-18 | MEETING-Project work/meetings | Review | Tien Thai | 1 | Stand up + meeting with Paul
2020-06-18 | Websocket-Doing the websocket integration | Implementation | Victor Hubbers | 1 | Merging with Mark
2020-06-18 | US-12-Statistics dashboard | Implementation | Katarzyna Strozykowska | 3 | working on the frontend implementation for the statistics dashboard
2020-06-18 | US-12-Statistics dashboard | Implementation | Tien Thai | 1.5 | working on the frontend implementation for the statistics dashboard
2020-06-18 | Frontend-Podium | Implementation | Vy Tran | 3.5 | Create podium screen
2020-06-18 | EXTRA-20%-ESLint | Implementation | Katarzyna Strozykowska | 4 | working on standard style for ESLint, analizing errors and fixing
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-06-19 | US-10-Result screen for moderator | Implementation | Tien Thai | 2.5 | Working on frontend connection - result screen for moderator
2020-06-19 | US-10-Result screen for moderator | Implementation | Vladyslav Petrykov | 2.5 | Working on frontend connection - result screen for moderator
2020-06-19 | Frontend-Podium | Implementation | Vy Tran | 3 | Connect to Vuex
2020-06-19 | Websocket-Doing the websocket integration | Implementation | Mark Kravchuk | 6 | Adding websocket functionality for frontend
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-06-20 | MEETING-Project work/meetings | Review | Victor Hubbers | 3 | stand up meeting
2020-06-20 | MEETING-Project work/meetings | Review | Katarzyna Strozykowska | 3 | stand up meeting
2020-06-20 | MEETING-Project work/meetings | Review | Vy Tran | 2.5 | stand up meeting
2020-06-20 | MEETING-Project work/meetings | Review | Vladyslav Petrykov | 1 | stand up meeting
2020-06-20 | MEETING-Project work/meetings | Review | Mark Kravchuk | 1 | stand up meeting
2020-06-20 | MEETING-Project work/meetings | Review | Tien Thai | 3 | stand up meeting
2020-06-20 | Frontend-Various little things | Implementation | Victor Hubbers | 3 | Frontend refinement (fconsole errors/addQuizQuestions page fits the screen better
2020-06-20 | XTRA-20%-AWS | Research | Victor Hubbers | 3 | Lookin in to how we can host frontent/backend on aws
2020-06-20 | XTRA-20%-AWS | Research | Vladyslav Petrykov | 3 | Research on AWS CI for project
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-06-21 | Frontend-Various little things | Implementation | Victor Hubbers | 2 | Frontend refinement (fconsole errors/addQuizQuestions page fits the screen better
2020-06-21 | AWS-CI | Implementation | Katarzyna Strozykowska | 2.5 | Set a sample project for AWS CI
2020-06-21 | AWS-CI | Implementation | Vladyslav Petrykov | 2.5 | Set a sample project for AWS CI
2020-06-21 | Frontend-Podium | Implementation | Vy Tran | 2 | Some refinement for podium screen
2020-06-21 | AWS-CI | Implementation | Victor Hubbers | 1.5 | Set a sample project for AWS CI
2020-06-21 | XTRA-20%-AWS | Research | Victor Hubbers | 2 | "implementing" hosting while researching/documenting it
2020-06-21 | Websocket-Doing the websocket integration | Implementation | Mark Kravchuk | 7 | Fixing bugs, adding websocket functionality for new pages, added new functionalities
2020-06-21 | EXTRA-20%-ESLint | Implementation | Katarzyna Strozykowska | 2 | writing scripts for frontend ESlint, basic implementation of the Eslint for backend
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-06-22 | MEETING-Project work/meetings | Review | Victor Hubbers | 3 | Merging and fixing everything
2020-06-22 | MEETING-Project work/meetings | Review | Katarzyna Strozykowska | 3 | Merging and fixing everything
2020-06-22 | MEETING-Project work/meetings | Review | Vy Tran | 3 | Merging and fixing everything
2020-06-22 | MEETING-Project work/meetings | Review | Vladyslav Petrykov | 3 | Merging and fixing everything
2020-06-22 | MEETING-Project work/meetings | Review | Mark Kravchuk | 3 | Merging and fixing everything
2020-06-22 | MEETING-Project work/meetings | Review | Tien Thai | 3 | Merging and fixing everything
2020-06-22 | XTRA-20%-AWS | Implementation | Victor Hubbers | 2 | Config with websockets and cleaning the database
2020-06-22 | Websocket-Doing the websocket integration | Review | Victor Hubbers | 1 | Testing from phones
2020-06-22 | Websocket-Doing the websocket integration | Review | Katarzyna Strozykowska | 1 | Testing from phones
2020-06-22 | Websocket-Doing the websocket integration | Review | Vy Tran | 1 | Testing from phones
2020-06-22 | Websocket-Doing the websocket integration | Review | Tien Thai | 1 | Testing from phones
2020-06-22 | Websocket-Doing the websocket integration | Review | Mark Kravchuk | 1 | Testing from phones
2020-06-22 | Frontend-Podium | Implementation | Vladyslav Petrykov | 2 | html/css/animations for Podium
2020-06-22 | AWS-CI | Implementation | Vladyslav Petrykov | 2 | connect gitlab with github + sample pipeline test
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-06-23 | DOC-1.2-Technical design | Documentation | Tien Thai | 1.5 | UI/UX research documentation
2020-06-23 | DOC-1.2-Technical design | Documentation | Tien Thai | 1 | Backend Database documentation
2020-06-23 | Frontend-Podium | Implementation | Vladyslav Petrykov | 1.5 | complete Podium screen
2020-06-23 | Frontend-Podium | Implementation | Vy Tran | 2 | complete Podium screen
2020-06-23 | MEETING-Project work/meetings | Review | Victor Hubbers | 1.5 | Meeting with Paul+ daily stand up
2020-06-23 | MEETING-Project work/meetings | Review | Katarzyna Strozykowska | 1.5 | Meeting with Paul+ daily stand up
2020-06-23 | MEETING-Project work/meetings | Review | Vy Tran | 1.5 | Meeting with Paul+ daily stand up
2020-06-23 | MEETING-Project work/meetings | Review | Vladyslav Petrykov | 1.5 | Meeting with Paul+ daily stand up
2020-06-23 | MEETING-Project work/meetings | Review | Mark Kravchuk | 1.5 | Meeting with Paul+ daily stand up
2020-06-23 | MEETING-Project work/meetings | Review | Tien Thai | 1.5 | Meeting with Paul+ daily stand up
2020-06-23 | AWS-CI | Implementation | Vladyslav Petrykov | 1 | Code build
2020-06-23 | DOC-1.2-Technical design | Documentation | Tien Thai | 3 | Api doc for backend
2020-06-23 | DOC-1.2-Technical design | Documentation | Katarzyna Strozykowska | 3 | Api doc for backend
2020-06-23 | DOC-1.2-Technical design | Documentation | Victor Hubbers | 4 | Manual for hosting
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-06-24 | MEETING-Project work/meetings | Review | Victor Hubbers | 2 | Meeting with Kris+ daily stand up
2020-06-24 | MEETING-Project work/meetings | Review | Katarzyna Strozykowska | 2 | Meeting with Kris+ daily stand up
2020-06-24 | MEETING-Project work/meetings | Review | Vy Tran | 2 | Meeting with Kris+ daily stand up
2020-06-24 | MEETING-Project work/meetings | Review | Vladyslav Petrykov | 2 | Meeting with Kris+ daily stand up
2020-06-24 | MEETING-Project work/meetings | Review | Mark Kravchuk | 2 | Meeting with Kris+ daily stand up
2020-06-24 | MEETING-Project work/meetings | Review | Tien Thai | 2 | Meeting with Kris+ daily stand up
2020-06-24 | DOC-1.2-Technical design | Documentation | Victor Hubbers | 5 | Manual for vuex
2020-06-24 | AWS-CI | Implementation | Vladyslav Petrykov | 1 | Properly sync github with gitlab
2020-06-24 | Frontend Refinements | Implementation | Vy Tran | 2 | Some refinement for podium screen, login screen
2020-06-24 | Frontend Refinements | Implementation | Vladyslav Petrykov | 1 | add quiz questions refinements
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-06-25 | MEETING-Project work/meetings | Review | Victor Hubbers | 2 | Meeting with Paul+ daily stand up
2020-06-25 | MEETING-Project work/meetings | Review | Katarzyna Strozykowska | 2 | Meeting with Paul+ daily stand up
2020-06-25 | MEETING-Project work/meetings | Review | Vy Tran | 2 | Meeting with Paul+ daily stand up
2020-06-25 | MEETING-Project work/meetings | Review | Vladyslav Petrykov | 2 | Meeting with Paul+ daily stand up
2020-06-25 | MEETING-Project work/meetings | Review | Mark Kravchuk | 2 | Meeting with Paul+ daily stand up
2020-06-25 | MEETING-Project work/meetings | Review | Tien Thai | 2 | Meeting with Paul+ daily stand up
2020-06-25 | EXTRA-20%-ESLint | Test | Victor Hubbers | 2 | Fix all eslint error
2020-06-25 | EXTRA-20%-ESLint | Test | Katarzyna Strozykowska | 2 | Fix all eslint error
2020-06-25 | EXTRA-20%-ESLint | Test | Vy Tran | 2 | Fix all eslint error
2020-06-25 | EXTRA-20%-ESLint | Test | Vladyslav Petrykov | 2 | Fix all eslint error
2020-06-25 | EXTRA-20%-ESLint | Test | Mark Kravchuk | 2 | Fix all eslint error
2020-06-25 | EXTRA-20%-ESLint | Test | Tien Thai | 2 | Fix all eslint error
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-06-26 | DOC-1.2-Technical design | Documentation | Victor Hubbers | 2 | Various changes in docs + sprint 1 reflection
2020-06-26 | DOC-1.2-Technical design | Documentation | Mark Kravchuk | 4 | Writing manual for websockets implementation
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-06-27 | DOC-1.2-Technical design | Documentation | Katarzyna Strozykowska | 1 | Sprint 2 reflection + ReadMe
2020-06-27 | DOC-1.2-Technical design | Documentation | Victor Hubbers | 2 | Update system overview + required software
2020-06-27 | DOC-1.2-Technical design | Review | Victor Hubbers | 2 | Discussing docs for handin
2020-06-27 | DOC-1.2-Technical design | Review | Katarzyna Strozykowska | 2 | Discussing docs for handin
2020-06-27 | DOC-1.2-Technical design | Review | Vy Tran | 2 | Discussing docs for handin
2020-06-27 | DOC-1.2-Technical design | Review | Vladyslav Petrykov | 2 | Discussing docs for handin
2020-06-27 | DOC-1.2-Technical design | Review | Mark Kravchuk | 2 | Discussing docs for handin
2020-06-27 | DOC-1.2-Technical design | Review | Tien Thai | 2 | Discussing docs for handin
2020-06-27 | DOC-1.1-Functional design | Review | Vy Tran | 1 | Transfer to markdown
2020-06-27 | PM-Project work/scrum board management | Project management | Vy Tran | 2 | add meeting notes to projects, write sprint retrospective
2020-06-27 | XTRA-20%-AWS | Test | Victor Hubbers | 2 | Testing 15+ same time users
2020-06-27 | XTRA-20%-AWS | Test | Katarzyna Strozykowska | 2 | Testing 15+ same time users
2020-06-27 | XTRA-20%-AWS | Test | Vy Tran | 2 | Testing 15+ same time users
2020-06-27 | -Hardware Interfacing, websocket protocol | Implementation | Mark Kravchuk | 2 | Tested the websocket intergration, fixed bugs
2020-06-27 | XTRA-20%-AWS | Test | Tien Thai | 2 | Testing 15+ same time users
2020-06-27 | AWS-CI | Documentation | Vladyslav Petrykov | 1 | Manual on how to connect AWS pipeline service to the project
2020-06-27 | -Hardware Interfacing, websocket protocol | Documentation | Mark Kravchuk | 1 | Writing RFC document
2020-06-27 | DOC-1.2-Technical design | Documentation | Vladyslav Petrykov | 1 | Changed diagram and format (from .docx to .md)
--------------- | -------------------------------------------- | -------------------------- | --------------------------------- | --------------- | -----------------------------------------------------------------------------------
2020-06-28 | DOC-3.0-Individual assignments | Documentation | Victor Hubbers | 3 | Individual documents
2020-06-28 | DOC-3.0-Individual assignments | Documentation | Mark Kravchuk | 8 | Individual documents
2020-06-28 | DOC-3.0-Individual assignments | Documentation | Tien Thai | 4 | Individual documents
2020-06-28 | DOC-3.0-Recommendation | Documentation | Tien Thai | 1 | Recommendation for backend (database)
2020-06-28 | DOC-3.0-Individual assignments | Documentation | Katarzyna Strozykowska | 3 | Individual documents
2020-06-28 | DOC-3.0-Individual assignments | Documentation | Vy Tran | 5 | Individual documents
2020-06-28 | DOC-3.0-Recommendation | Documentation | Tien Thai | 2 | Final preparations for handin + recommendations
2020-06-28 | DOC-3.0-Recommendation | Documentation | Vy Tran | 2 | Final preparations for handin + recommendations
2020-06-28 | DOC-3.0-Recommendation | Documentation | Vladyslav Petrykov | 2 | Final preparations for handin + recommendations
2020-06-28 | DOC-3.0-Recommendation | Documentation | Victor Hubbers | 2 | Final preparations for handin + recommendations
2020-06-28 | DOC-3.0-Recommendation | Documentation | Mark Kravchuk | 2 | Final preparations for handin + recommendations
2020-06-28 | DOC-3.0-Recommendation | Documentation | Katarzyna Strozykowska | 2 | Final preparations for handin + recommendations
Usage instructions
1 Make sure to fill in the DATA tabs below with the correct information
2 Use the sheet on the left to register working hours
3 View the overview tabs (automatically updated)

## DATA - User stories
ID | Description | ID-Description
START | Startup of project | START-Startup of project
START | Vuex version 0 | START-Vuex version 0
MEETING | Project work/meetings | MEETING-Project work/meetings
DOC-0.1 | Plan of Approach | DOC-0.1-Plan of Approach
DOC-1.1 | Functional design | DOC-1.1-Functional design
DOC-1.2 | Technical design | DOC-1.2-Technical design
US-14 | Answering questions | US-14-Answering questions
US-9 | Creating dashboard | US-9-Creating dashboard
US-1 | Creating quiz | US-1-Creating quiz
US-6 | Adding multiple choice questions | US-6-Adding multiple choice questions
US-5 | Invitation screen | US-5 Implement invitation screen
US-2 | Edit quiz | US-2-Edit quiz
US-17 | Login screen | US-17-Login screen
US-13 | Result screen for moderator | US-13-Result screen for moderator
US-17-backend | Login/logout functionality | US-17-backend-Login/logout functionality
Backend | backend for the project | Backend-backend for the project
US-7 | Timing functionality | US-7-Timing functionality
CNCT | connecting backend with frontend | CNCT-connecting backend with frontend
Websocket | Doing the websocket integration | Websocket-Doing the websocket integration
US-4 | Customize quiz- logo | US-4-Customize quiz- logo
US-18 | Result screen for player | US-18-Result screen for player
Image | Image uploading | Image-Image uploading
XTRA-20% | Testing | XTRA-20%-Testing
XTRA-20% | Design | XTRA-20%-Design
EXTRA-20% | ESLint | EXTRA-20%-ESLint
API | connection frontend | API-connection frontend
Presentation | with client | Presentation-with client
US-12 | Statistics dashboard | US-12-Statistics dashboard
US-10 | Result screen for moderator | US-10-Result screen for moderator
XTRA-20% | AWS | XTRA-20%-AWS
Frontend | Various little things | Frontend-Various little things
AWS | CI | AWS-CI
Frontend | Podium | Frontend-Podium
Frontend Refinements
PM | Project work/scrum board management | PM-Project work/scrum board management
| Hardware Interfacing, websocket protocol | -Hardware Interfacing, websocket protocol
DOC-3.0 | Individual assignments | DOC-3.0-Individual assignments
DOC-3.0 | Recommendation | DOC-3.0-Recommendation
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
Usage instruction
Enter ID en Description
Note: Column ID-Description is automatically filled in

## Overview - tasks
Sum of Hours
| Research | Total
START-Startup of project | 98.5 | 98.5
XTRA-20%-Testing | 8 | 8
EXTRA-20%-ESLint | 2 | 2
XTRA-20%-AWS | 8 | 8
Total | 116.5 | 116.5
Overview userstories
Hours per category
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Usage instructions
1. "Right-click" -> "Refresh" to refresh the pivot table on the left
2. Make sure to filter out blank lines in the slicer below

## DATA - Type tasks
Type tasks
Design
Documentation
Implementation
Test
Review
Research
Project management
Usage instruction
Enter type of tasks
Note: Try to keep this list short!

## Personal Data
Name | Tel | Email
Vy Tran | +31 6446 17956 | 463298@student.saxion.nl
Tien Thai | +31 6873 03582 | 460592@student.saxion.nl
Mark Kravchuk | +38 0957610842 | 460888@student.saxion.nl
Vladyslav Petrykov | +38 0972307557 | 461157@student.saxion.nl
Victor Hubbers | +31 6 46564624 | 469487@student.saxion.nl
Katarzyna Strozykowska | +31 6 49223525 | 472064@student.saxion.nl

## Overview - employees
Sum of Hours
Documentation | 18
Katarzyna Strozykowska | 18
MEETING-Project work/meetings | 3
DOC-0.1-Plan of Approach | 4
DOC-1.2-Technical design | 4
EXTRA-20%-ESLint | 2
DOC-3.0-Individual assignments | 3
DOC-3.0-Recommendation | 2
Implementation | 82
Katarzyna Strozykowska | 82
START-Startup of project | 9
US-9-Creating dashboard | 17
US-6-Adding multiple choice questions | 4
US-5 Implement invitation screen | 3
Backend-backend for the project | 27.5
CNCT-connecting backend with frontend | 6
US-4-Customize quiz- logo | 2
EXTRA-20%-ESLint | 6
US-12-Statistics dashboard | 5
AWS-CI | 2.5
Test | 4
Katarzyna Strozykowska | 4
EXTRA-20%-ESLint | 2
XTRA-20%-AWS | 2
Review | 64.5
Research | 36.5
Katarzyna Strozykowska | 36.5
START-Startup of project | 34.5
EXTRA-20%-ESLint | 2
Total | 205
Overview employees
Hours per userstory
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Usage instructions
1. "Right-click" -> "Refresh" to refresh the pivot table on the left
2. Make sure to filter out blank lines in the slicer below
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.